## Sheet1
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
A. SOCIAL SECTOR:
>Mun. Building Construction- Loan Pymt. | Duero, Bohol | 1,809,635.57 | Jan. 2017 | Dec. 2017 | 98% | 1,768,946.31 |  | Completed
BARANGAY PROJECTS:
>Concreting of Barangay Road | Alejawan, Duero | 150,000.00 | April 22, 2017 | May 17, 2017 | 100% | 134,980.20 |  | Completed
> Completion of Muti-Purpose Hall | Angilan, Duero | 150,000.00 | October 3, 2017 | Nov. 20, 2017 | 100% | 149,896.38 |  | Completed
> Concreting of Barangay Road | Anibongan, Duero | 150,000.00 | October 3, 2017 | Nov. 2, 2017 | 100% | 149,860.00 |  | Completed
> Improvement of Waterwork System | Bangwalog, Duero | 150,000.00 | Jan. 2017 | Dec. 2017 |  |  |  | On-going
> Concreting of Farm to Market Road | Cansuhay, Duero | 150,000.00 | April 16, 2017 | May 10, 2017 | 100% | 135,000.00 |  | Completed
> Completion of Multi-Purpose Hall | Danao, Duero | 150,000.00 | Oct. 3, 2017 | Nov. 2, 2017 | 100% | 144211.5 |  | Completed
> Rehabilitation of Basketball Court of
Sitio Wangonhan | Duay, Duero | 150,000.00 | Oct. 3, 2017 | Nov. 2, 2017 | 100% | 149587.59 |  | Completed
> Completion of Multi-Purpose Hall | Guinsularan, Duero | 150,000.00 | Jan. 2017 | Dec. 2017 |  |  |  | On-going
> Completion of Multi-Purpose Hall | Imelda, Duero | 150,000.00 | Jan. 2017 | Dec. 2017 |  |  |  | On-going
> Completion of Multi-Purpose Hall | Itum, Duero | 150,000.00 | Jan. 2017 | Dec. 2017 |  |  |  | On-going
> Completion Of Covered Court | Langkis, Duero | 150,000.00 | Jan. 2017 | Dec. 2017 |  |  |  | On-going
Sub-Total |  | 3459635.57 |  |  | P | 2632481.98
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
> Rehabilitation of Barangay Stage | Lobogon, Duero | 150,000.00 | Oct. 3, 2017 | Nov, 20, 2017 | 100% | 144,948.59 |  | Completed
> Completion of Multi-Purpose Hall | Madua Norte, Duero | 150,000.00 | Jan. 2017 | Dec. 2017
> Concreting of Barangay Road | Madua Sur, Duero | 150,000.00 | April 30,2017 | May 20, 2017 | 100% | 149,903.20 |  | Completed
> Concreting of Barangay Road | Mambool, Duero | 150,000.00 | April 22, 2017 | May 11,2017 | 100% | 134,980.20 |  | Completed
> Completion of Covered Court | Mawi, Duero | 150,000.00 | April 30, 2017 | June 27, 2017 | 100% | 149,404.30 |  | Completed
> Concreting of Pathway Going to Sitio Ilaud | Payao, Duero | 150,000.00 | Oct. 3, 2017 | Nov. 1, 2017 | 100% | 149,598.88 |  | Completed
> Concreting of Farm to Market Road | San Antonio, Duero | 150,000.00 | April 29,2017 | May 8, 2017 | 100% | 149,903.21 |  | Completed
> Construction of New Basketball Court | San Isidro, Duero | 150,000.00 | April 16, 2017 | May 12, 2017 | 100% | 135000 |  | Completed
> Concreting of Barangay Road | San Pedro, Duero | 150,000.00 | April 22, 2017 | May 16, 2017 | 100% | 134,980.20 |  | Completed
> Completion of Bleacher | Taytay, Duero | 150,000.00 |  | Dec. 2017 |  |  |  | On-going
> Purchase of Heavy Equipment for FMR | Duero, Bohol | 2,000,000.00 |  | Dec. 2017 |  | 9,710.40 |  | On-going
> KALAHI-CIDSS Sub-Project Implementation-
Mun-Counterpart | Duero, Bohol | 500,000.00 |  | Dec. 2017 |  | 500,000.00 |  | Completed
> Purchase of Lot for Housing Project | Duero, Bohol | 300,000.00 | May 2017 | Dec. 11, 2017 | 100% | 240,000.00 |  | Completed
Sub-Total |  | 4300000 |  |  | P | 1898428.98
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
B. ENVIRONMENTAL DEVELOPMENT
1. Sustenence of Solid Waste Mgt. Poject | Duero, Bohol | 1,200,000.00 | Jan. 2017 | Dec. 2017 | 55% | 665,283.38 |  | On-going
C. ECONOMIC SECTOR
> Maintenance of Heavy Equipment for FMR | Duero, Bohol | 300,000.00 | Jan. 2017 | Dec. 2017 | 91% | 271,988.50 |  | On-going
> Municipal Agriculture Program | Duero, Bohol | 150,000.00 | Jan. 2017 | Dec. 2017 | 97% | 145,140.00 |  | Completed
> Coastal Resource Mngt. Program | Duero, Bohol | 150,000.00 | Jan. 2017 | Dec. 2017 | 85.59% | 128391.05 |  | On-going
> Development of Waterworks System | Duero, Bohol | 500,000.00 | [5 empty] | Not Yet Started
> Acquisition of Lot for Establishment
of New Slaughterhouse | Duero, Bohol | 350,000.00 | March 2017 | Dec. 28, 2017 | 100% | 338,049.92 |  | Completed
D. INFRASTRACTURE
> Repair of Municipal Road | Duero, Bohol | 300,000.00 | June 11, 2017 | Aug. 8, 2017 | 100% | 299,899.65 |  | Completed
> Construction of Drainage Canal of
Municipal Road | Duero, Bohol | 367,604.43 | June 11, 2017 | July 25, 2017 | 100% | 366,086.86 |  | Completed
> Fencing of Mun. Agricultur Office
Premises | Duero, Bohol | 150,000.00 | June 11, 2017 | Aug. 9, 2017 | 100% | 149,038.86 |  | Completed
> Integrated National Resources Environment
Management Project (INREMP)
Municipal Counterpart | Duero, Bohol | 1,400,000.00 | [5 empty] | Waiting for the no
objection letter from
ADB
Sub-Total |  | 4867604.43 |  |  |  | 2363878.22
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
B. ECONOMIC SECTOR (Contd)
> Development of Municipal Memorial Park | Duero, Bohol | 500,000.00 | June 11, 2017 | Sept. 11, 2017 | 100% | 499912.34 |  | Completed
> Improvement of Abueva Family Art Gallery | Duero, Bohol | 200,000.00 | Nov. 2, 2017 | Dec. 28, 2017 | 50% | 95855.65 |  | On-going
Sub-Total |  | 700000 |  |  |  | 595767.99
GRAND TOTAL |  | 13327240 |  |  |  | 7490557.17
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this document.
CONCHITA C. MACAS |  | NIDA B. MADRID |  |  |  | CONRADA C. AMPARO
Municipal Budget Officer |  | Municipal Accountant |  |  |  | Municipal Mayor