## 2ndQtr2017
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
A. SOCIAL SECTOR:
> Mun. Building Construction - Loan Pymt | Duero, Bohol | 1809635.57 | Jan, 2017 | Dec. 2017 | 50% | 889650.32 |  | On going
> Assistance to Disadvatange Municipality
(ADM) Municipal Counterpart | Duero , Bohol | 1000000 | Jan, 2017 | Dec. 2017 |  |  |  | Not yet started
. BARANGAY PROJECTS:
> Concreting of Barangay Road | Alejawan, Duero | 150000 | April-22-2017 | May-17-2017 | 100% | 134980.2 |  | Completed
> Completion of Multi-Purpose hall | Angilan , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | On bidding process
> Concreting of Barangay Road | Anibongan, Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | On bidding process
> Improvement of Waterwork System | Bangwalog, Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | Not yet started
> Concreting of Farm to Market Road | Cansuhay , Duero | 150000 | April-16-2017 | 2017-05-10 | 100% | 135000 |  | Completed
> Completion of Multi-Purpose hall | Danao , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | On bidding process
> Rehabilitation of Basketball Court of
Sitio Wangonhan | Duay , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | On bidding process
> Completion of Multi-Purpose hall | Guinsularan , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | Not yet started
> Completion of Multi-Purpose hall | Imelda , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | Not yet started
> Completion of Multi-Purpose hall | Itum , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | Not yet started
> Completion of Covered Court | Langkis , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | Not yet started
> Rehabilitation of Brgy Stage | Lobogon , Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | On bidding process
> Completion of Multi-Purpose hall | Madua Norte, Duero | 150000 | Jan, 2017 | Dec. 2017 |  |  |  | Not yet started
Sub-Total |  | 4759635.57 |  |  | P | 1159630.52
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
A. SOCIAL SECTOR (Contd)
> Concreting of Barangay Road | Madua Sur, Duero | 150000 | April-30-2017 | 2017-05-20 | 100% | 149903.2 |  | Completed
> Concreting of Barangay Road | Mambool , Duero | 150000 | April-22-2017 | 2017-05-11 | 100% | 134980.2 |  | Completed
> Completion of Covered Court | Mawi , Duero | 150000 | April-30-2017 | 2017-06-27 | 100% | 149404.3 |  | Completed
> Concreting of Pathway going to Sitio Ilaud | Payao , Duero | 150000 |  | Dec. 2017 |  |  |  | On Bidding Process
> Concreting of Farm to Market Road | San Antonio , Duero | 150000 | April-29-2017 | 2017-05-08 | 100% | 149903.21 |  | Completed
> Construction of New Basketball Court | San Isidro , Duero | 150000 | April-16-2017 | 2017-05-12 | 100% | 135000 |  | Completed
> Concreting of Barangay Road | San Pedro , Duero | 150000 | April-22-2017 | 2017-05-16 | 100% | 134980.2 |  | Completed
> Completion of Bleacher | Taytay , Duero | 150000 |  | Dec. 2017 |  |  |  | Not yet started
> Purchase of Heavy Equipment for FMR | Duero , Bohol | 1400000 |  | Dec. 2017 |  |  |  | Not yet started
> KALAHI-CIDSS Sub Project Implmentation -
Mun-Counterpart | Duero , Bohol | 500000 |  | Dec. 2017 |  |  |  | Not yet started
> Purchase of Lot for Housing Project | Duero , Bohol | 300000 |  | Dec. 2017 |  |  |  | Not yet started
B. ENVIRONMENTAL DEVELOPMENT
1. Sustenance of Solid Wste Mgt. Proj. | Duero , Bohol | 1200000 | Jan, 2017 | Dec. 2017 | 21.7% | 255138.68 |  | On Going
C. ECONOMIC SECTOR "Contd)
> Maintenance of Heavy Equipment for FMR | Duero , Bohol | 300000 | Jan, 2017 | Dec. 2017 | 44% | 131529 |  | On Going
> Municipal Agriculture Program | Duero , Bohol | 150000 | Jan, 2017 | Dec. 2017 | 37.25% | 55870 |  | Not yet started
Sub-Total |  | 5050000 |  |  | P | 1296708.79
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
> Coastal Resource Management Program | Duero , Bohol | 150000 | Jan. 2017 | Dec. 2017 | 7.7% | 11572 |  | On going
> Development of Waterworks System | Duero , Bohol | 500000 |  | Dec. 2017 |  |  |  | Not yet started
> Acquisition of Lot for Establishment of
New Slaughterhouse | Duero , Bohol | 350000 |  | Dec. 2017 |  |  |  | Not yet started
D. INFRASTRUCTURE
> Repair of Municipal Road | Duero , Bohol | 300000 | June-11-2017 | Aug.-11-2017 | 10% | (No billing yet) |  | On going
> Construction of Drainage Canal of Munici-
pal Road |  | 367604.43 | June-11-2017 | Sept.-01-2017 | 40% | (No billing yet) |  | On going
> Fencing of Mun. Agriculture Office Premises | Duero , Bohol | 150000 | June-11-2017 | July-25-2017 | 80% | (No billing yet) |  | On going
> Philippine Rural Dev't Project (PRDP) -
Municipal Counterpart | Duero , Bohol | 500000 |  | Dec. 2017 |  |  |  | Not yet started
> Integrated National Resources Environment
Management Project (INREMP)
Municipal Counterpart | Duero , Bohol | 500000 |  | Dec. 2017 |  |  |  | Not yet started
Sub-Total |  | 2817604.43 |  |  | P | 11572
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2017
Municipality of : | DUERO, BOHOL
Program or |  |  |  | Target | Project Status |  | No. of
Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extension,if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
B. ECONOMIC SECTOR "Contd)
> Development of Municipal Memorial Park | Duero , Bohol | 500000 | June-11-2017 | Sept.-11-2017 | 60% | (No billing yet) |  | On going
> Improvement of Abueva Family Art Gallery | Duero , Bohol | 200000
Sub-Total |  | 700000 |  |  | P | 0
GRAND TOTAL |  | 13327240 |  |  | P | 2467911.31
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this document.
CONCHITA C. MACAS | [5 empty] | CONRADA C. AMPARO
Municipal Budget Officer | [5 empty] | Municipal Mayor